## Introduction
Task list for ResourceContracts and OpenLandContracts
What is this? | This workbook is meant to help manage and piroritize the user stories and features of the ResourceContracts and OpenLandContracts projects
How to use and read this document? | Before project start: The Project Manager at NRGI is responsible for managing and maintaining the product backlog of user stories as prioritised by the members of the consortium - NRGI, CCSI and WB.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells than you can edit use a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## NRGI Product backlog
Product Backlog
| Organizations | NRGI, CCSI and World Bank
| Project | ResourceContracts and Open Land Contracts
Scrum Master
Product Owner
Story ID | Title | User story | Priority (%) | Sprint #
1 | Authentication web page | As a user I need a start page to authenticate myself into the administrative interface.
2 | Annotation interface | As a user I need a administrative interface from where I can annotate contracts using a standardised template. Review the current annotation process and tools, propose alternative tools (such as Hypothesis.io or Rap Genius) to improve the process and suggest how human-created annotations can be combined with machine tagging of the text within contracts.
3 | Front end | As a user I need a website that displays contracts tagged <land contracts> on Open Land Contracts
4 | Front end | As a user I need a website that displays contracts tagged <extractives> on ResoureContracts
5 | Full html text search | As a user I need to be able to search html text within the contracts - even if the original is a scanned PDF
6 | Access to document repository | As a user I need a page with access to a full overview of the contracts available
7 | Provenance in contract view | As a user I need to be able to easily access the original view of the PDF contract when I am browsing the html text
8 | Filtering | As a user I would like to be able to search across three layers of content: i. a) metadata with basic data, ii. b) human-generated annotations of the contracts in accordance with annotation schema and iii. c) the full OCR’ed contract text
9 | Category pages | Dynamic overview pages to provide easier access to contracts users are interested in, either based on countries, resources or other metadata and annotation data along with dynamic statistics to show recent trends.
10 | API | As a user I need a well documented API that allow me to easily reuse the data
11 | Low bandwith capacity | As a user I to be able to access the site without having access to high speed internet
12 | High bandwith capacity | As a user I need to be able to access the site with nice design and interation, while not being limited by low-bandwith users
13 | Management interface for country subsites | As a government official in a pilot country I need to be able to easily manage users, load and annotate contracts
14 | Front end interface for country subsites | As a government official in a pilot country I need to have a website with national features on the front end incl. visual identity and blog
15 | Expanded search | As a user I need to search and filter across contract a) content, b) annotations and c) metadata. This should include free text search on content, fuzzy matching of key terms, autocomplete search, and similarity recommendations. Example: As a researcher I would like a table with all the <Royalty Clauses>, for all <gold> contracts, from <2000 – 2014> in <Africa>. The result of the search should be available as clear interface and as download in an open format.
16 | Pinning | As a users I should have the ability to select and cache individual clauses across contracts for comparison. These clauses should be possible to store in session and export to excel or PDF as a report. Example: I wish to compare stabilization clauses. I search contracts for clauses tagged as such, pin those clauses for later comparison and export a report of the pinned html, data and associated metadata.
17 | Internationalization | As a user I need to experience a single language user experience across three supported languages: English, French and Spanish. Eg. automatic language detection based on Accept-Language (set in user’s browser).
18 | Content from African Mining Legislative Atlas | As a user I would like to see which mining laws have authorised the specific contract, based on data pulled from African Mining Legislative Atlas
19 | Upgrade of existing country pilot | As a user I would like to access the countract transparency site - http://www.contratsminiersguinee.org - easily using the new features developed for ResourceContracts
20 | Expand document retrieval | As a user I would like to access an extensive selection of contracts. Current document retrieval method is manual. However, NRGI is currently testing automatic document search in order to scale contract retrieval. The vendor will work to implement a load API, with verification and authentication mechanisms built in – for example to enable human review of newly sourced contracts from internal security exchanges (eg. 10-K’s from the SEC’s EDGAR).
21 | Content mining | As a user I would like to have spatial information on the concession area related to the contract (typically released in Annex B), or similar rich content. Vendor will propose methods and scenarios for developing mining of content within contracts for important data points. Two examples would be to extract data for fiscal modeling and GIS-specific data to link to other GIS concession and project data.
22 | Review of annotation schema | As a user I need to be able to easily work with data from ResourceContracts and other data sources in the extractive sector. This means having a high degree of interoperability around key data points. This could include adjustments to current annoutation template through standardization and interoperability with other data sources, including the African Mining Legislation Atlas. For background, the vendor will be provided an extractive data taxonomy map, which identifies the stakeholders and the key taxonomies that are in question.
23 | Mobile responsiveness | As a user I would like to be able to access and use RC and OLC seamlessly from a mobile device.
24 | Multiple languages for contracts | As a user I need to have an easy way to engage with contracts in multiple languages (English, French, Spanish)
25 | Multiple languages for annotations | As a user I need to have an easy way to engage with annotations in multiple languages (English, French, Spanish), and to be able to toggle between the translations of such annotations
26 | Search feature | As a user I need to be able to find key terms or sections within contracts.
27 | Search terms across spelling differences and across languages | As a user I need to be able to search terms across contracts presented in multiple languages and spelling methods (US vs. Brittish English). As an example I need search features that incorporate different spellings of "stabilization" so that I can compare stabilization clauses across contracts in US-English, British English and French. A solution to this could be fuzzy mathing or a codelist of faceted/grouped terms aross languages.
28 | Identifying 'webs' of contracts | As a user I need to be able to see whether any other contracts are linked to the same investment project covered by the contract I am reading. For example, I may be reading the land lease for an oil project but there may be amendments, social agreements, forestry management plans, or other contracts concerning other aspects of that oil project, such as contracts that talk about work obligations, fiscal provisions, environmental and social obligations, etc.
29 | Explanations of types of contract clauses | As a user I would like to be able to read short explanations of various types of contractual provisions, that are linked to the annotations themselves (So that, for example, the annotation of a stabilization clause could somehow be linked to a brief explanation of what a stabilization clause is)
30 | Linking an annotation to multiple clauses | As a user, I need an annotation that refers to multiple clauses of a contract to be linked to each of those clauses in the primary pdf document (as opposed to right now, where the annotation is only physically linked to one of the articles referred to).
31 | Potential for trusted partners to add their own annotations | As a user, I want to develop a filter that could be applied if other users ("trusted partners"), for example a civil society group, want to add their own annotations of the contracts.
32 | Hosting of additional resources | As a user, I need to be able to add guidance documents to the site, to assist in user understanding of the contracts.
33 | Hosting additional documents | As a user, I need to be able to upload annotated versions of documents other than contracts, such as AIM summaries of contracts that are not public. But these documents also have to be clearly identified as different from a contract itself.
Note on A10: Olivier Gérardin: A unique ID to refer to this story. Doesn't have to be numeric.
Note on B10: Olivier Gérardin: A short title just enough to recall the story.
Note on C10: Olivier Gérardin: (from product owner) Description of the user story in common language. Keep it short (one or wo sentences). Usually formatted as: "As a <role> I want to <function> so that <benefit>".
Note on D10: Olivier Gérardin: (from product owner) Priority of this story. Use an open scale so you can always move priorities later.
Note on E10: Olivier Gérardin: Fill in after Sprint Planning Meeting

## Sprint 1 (example)
Sprint #1Tracking Sheet
|  | Project | ResourceContracts and Open Land Contracts
|  | Sprint # | 1
|  | Start date | 2015-06-01
|  |  |  | week 1 |  |  |  |  | week 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Task ID | Story ID | Description | Initial estimate | 2015-06-01 | 2015-06-02 | 2015-06-03 | 2015-06-04 | 2015-06-05 | 2015-06-08 | 2015-06-09 | 2015-06-10 | 2015-06-11 | 2015-06-12
1 | 1
3 | 1
6 | 1
2 | 1
5 | 1
4 | 1
|  | Remaining units (actual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Remaining units (ideal) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 0 | 0
[12 empty] | 10 | 0
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on C20: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on C21: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on D20: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.